## Harsh
Wildriver Pending Tasks with ETA
Sl. No. | Section | Task | ETA
1 | Dealer | Stock check | 16/05/2014
2 | Dealer | Place/Reserve/Print Order | 19/05/2014
3 | Dealer | Display Placed/Reserved Orders (Current Order Status) | 20/05/2014
4 | Dealer | Reserved Order Page (Place Order/ Cancel Reserve/ Place+ Print) | 21/05/2014
5 | Dealer | Receive Goods | 22/05/2014
6 | Dealer | Order History display & print | 24/05/2014
7 | Dealer | Dealer Section Update Details | 25/05/2014
8 | Admin | Stock Manager - History | 27/05/2014
9 | Admin | Search task in all pages | 29/05/2014

## Nandish
Wildriver Pending Tasks with ETA
Sl. No. | Section | Task | ETA
1 | Admin | Stock levels table in homepage & commit selected to order. | 19/05/2014
2 | Admin | Display the POs (Transit stk table in pg.1 & pg.5) | 21/05/2014
3 | Admin | PO related Tasks (Print, Receive) | 22/05/2014
5 | Admin | Display Dealer Orders | 25/05/2014
6 | Admin | Dispatch & Print Dealer Orders | 26/05/2014
7 | Dealer | Search functionality in all pages | 30/05/2014